## WCC Progress
Wave City Club- Progress Against Milestones
Report Generated on: 14-05-2026
Months Covered: March 2026, April 2026, May 2026
Milestone | Block | Target to be complete by May-2026 | Target - March-2026 | % work done- March Status | Achieved- March 2026 | Weightage- March | Weighted %- March | Target - April-2026 | % work done- April Status | Achieved- April 2026 | Weightage- April | Weighted %- April | Target - May-2026 | % work done- May Status | Achieved- May 2026 | Weightage- May | Weighted %- May | Responsible | Delay Reason
Milestone-01 | Block 1 (B1) Banquet Hall | No targets | Terrace Waterproofing | 100% | Target exceeded (75% > 50%) | 100 | 100% | Terrace Waterproofing | 100% | Target exceeded (75% > 50%) | 100 | 100% | No targets
Milestone-02 | Fine Dine | No targets | Terrace Waterproofing | 100% | Target exceeded (75% > 50%) | 100 | 100% | Terrace Waterproofing | 100% | Target exceeded (75% > 50%) | 100 | 100% | No targets
Milestone-03 | Block 5 (B5) Admin + Member Lounge+Creche+Av Room + Surveillance Room +Toilets | Terrace Waterproofing | External Plaster | 100% | Target achieved (50% complete) | 100 | 100% | External Plaster | 100% | Target achieved (100% complete) | 100 | 100% | Terrace Waterproofing
Milestone-04 | Block 6 (B6) Toilets | Terrace Waterproofing | No targets | 0% | Activity not found in tracker | 100 | 0% | Terrace Work | 100% | Target achieved (100% complete) | 100 | 100% | Terrace Waterproofing
Milestone-05 | Block 7(B7) Indoor Sports | Terrace Waterproofing | Brick Work GF | 100% | Target achieved (100% complete) | 100 | 100% | External Plaster | 100% | Target achieved (100% complete) | 100 | 100% | Terrace Waterproofing
Milestone-06 | Block 9 (B9) Spa & Saloon | External Plaster | No targets | 0% | Activity not found in tracker | 100 | 0% | Brick Work GF | 0% | 0% completed (Target: 100%) | 100 | 0% | External Plaster
Milestone-07 | Block 8 (B8) Squash Court | External Plaster | Brick Work GF | 10% | 10% completed (Target: 50%) | 100 | 10% | Brickwork GF | 0% | Activity not found in tracker | 100 | 0% | External Plaster
Milestone-08 | Block 2 & 3 (B2 & B3) Cafe & Bar | Terrace Waterproofing | No targets | 0% | Activity not found in tracker | 100 | 0% | Brickwork | 0% | Activity not found in tracker | 100 | 0% | Terrace Waterproofing
Milestone-09 | Block 4 (B4) Indoor Swimming Pool Changing Room & Toilets | Terrace Work | GF Roof Slab Reinforcement | 100% | Target achieved (100% complete) | 100 | 100% | GF Roof Slab Casting | 40% | 40% completed (Target: 100%) | 100 | 40% | Terrace Work
Milestone-10 | Block 11 (B11) Guest House | Brick Work GF | No targets | 0% | Activity not found in tracker | 100 | 0% | Plinth Beam Concreting | 20% | 20% completed (Target: 100%) | 100 | 20% | Brick Work GF
Milestone-11 | Block 10 (B10) Gym | No targets | GF Roof Slab Casting | 100% | Target achieved (100% complete) | 100 | 100% | Brick Work GF | 50% | 50% completed (Target: 100%) | 100 | 50% | No targets
AVERAGE WEIGHTED % | [6 empty] | 55.5% |  |  |  |  | 55.5%