## Time Delivery Milestones
Veridia Time Delivery Milestones Report - Q4 (March, April, May) 2026
Report Generated on: 30-04-2026
Tower 6 Structure Work Milestone Progress Against Milestones
Milestone | Activity | Target | % Work Done against Target-Till March | % Work Done against Target-Till April | % Work Done against Target-Till May | Weightage | Weighted Delay against Targets | Total achieved | Target achieved in March | Target achieved in April | Target achieved in May | Delay Reasons_May 2026
01 | Slab Casting |  |  |  |  | 100
Total | [6 empty] | 0%
Tower 5 Finishing Milestone Progress Against Milestones
Milestone | Activity | Target | % Work Done against Target-Till March | % Work Done against Target-Till April | % Work Done against Target-Till May | Weightage | Weighted Delay against Targets | Target achieved in March | Target achieved in April | Target achieved in May | Total achieved | Delay Reasons_May 2026
Tower 6 Finishing Milestone Progress Against Milestones
Milestone | Activity | Target | % Work Done against Target-Till March | % Work Done against Target-Till April | % Work Done against Target-Till May | Weightage | Weighted Delay against Targets | Total achieved | Target achieved in March | Target achieved in April | Target achieved in May | Delay Reasons_May 2026
01 | Floor Tiling | 80 Flats (33-March, 47-April) | 0.0% |  |  | 25 | 0.0% | 0 Flats | 0 out of 33 Flats | 0 out of 47 Flats | 0 out of 0 Flats
02 | Wall Tiling | 81 Flats (49-March, 32-April) | 0.0% |  |  | 25 | 0.0% | 0 Flats | 0 out of 49 Flats | 0 out of 32 Flats | 0 out of 0 Flats
03 | Installation of Rear & Front balcony UPVC Windows | 88 Flats (6-March, 30-April, 52-May) | 0.0% |  |  | 25 | 0.0% | 0 Flats | 0 out of 6 Flats | 0 out of 30 Flats | 0 out of 52 Flats
04 | EL-Second Fix | 116 Flats (24-March, 64-April, 28-May) | 0.0% |  |  | 25 | 0.0% | 0 Flats | 0 out of 24 Flats | 0 out of 64 Flats | 0 out of 28 Flats
Total | [6 empty] | 0.0%
Tower 7 Finishing Milestone Progress Against Milestones
Milestone | Activity | Target | % Work Done against Target-Till March | % Work Done against Target-Till April | % Work Done against Target-Till May | Weightage | Weighted Delay against Targets | Total achieved | Target achieved in March | Target achieved in April | Target achieved in May | Delay Reasons_May 2026
01 | Installation of wardrobes and cabinets | 42 Flats (6-March, 18-April, 18-May) | 100.0% |  |  | 25 | 25.0% | 7 Flats | 7 out of 6 Flats | 0 out of 18 Flats | 0 out of 18 Flats
02 | Installation of doors | 43 Flats (7-March, 18-April, 18-May) | 100.0% |  |  | 25 | 25.0% | 7 Flats | 7 out of 7 Flats | 0 out of 18 Flats | 0 out of 18 Flats
03 | C-Painting First Coat | 2 Flats (1-March, 1-April) | 100.0% |  |  | 25 | 25.0% | 2 Flats | 2 out of 1 Flats | 0 out of 1 Flats | 0 out of 0 Flats
04 | ST-Painting First Coat | 4 Flats (2-March, 2-April) | 100.0% |  |  | 25 | 25.0% | 4 Flats | 4 out of 2 Flats | 0 out of 2 Flats | 0 out of 0 Flats
Total | [6 empty] | 100.0%
External Development Milestone: Progress Against Milestones
Milestone | Activity | Target | % Work Done against Target-Till March | % Work Done against Target-Till April | % Work Done against Target-Till May | Weightage | Weighted Delay against Targets | Target achieved in March | Target achieved in April | Target achieved in May | Total achieved | Delay Reasons_May 2026